## Cover
Agentic Workbench
Production Readiness Work Plan
Version: 2026-07-01 ¦ Status: Approved ¦ Team: 2–4 developers ¦ Timeline: 3–6 months to MVP
HOW TO USE THIS TRACKER
1 Tracker — full hierarchical activity list. Assign owners, set status, track % done. Rows are grouped: click the +/– controls on the left to collapse/expand phases and workstreams.
2 Summary — phase-level view with activity counts, priority, and a rough 24-week timeline.
3 Critical Path — the 6 items that will slip the launch date if delayed. Start these on Day 1.
4 Open Questions — the 6 decisions that must be resolved in the Phase 2 scoping workshop.
STATUS VALUES
Not Started → work has not begun
In Progress → actively being worked on
Complete → done and verified
Blocked → waiting on a dependency or blocker
On Hold → intentionally paused
PRIORITY KEY
Critical → delay slips the project deadline or blocks other work
High → must be in v1; significant risk or user impact if deferred
Medium → should be in v1; manageable if deferred to early v2
Low → nice to have; can be deferred without impact

## Tracker
ID | Activity / Workstream / Phase | Owner | Priority | Start Wk | End Wk | Status | % Done | Notes
Phase 0 — START IMMEDIATELY & RUN IN PARALLEL
0.0 | Knowledge Transfer |  |  | 1 | 3 | Not Started | 0 | Runs in parallel with all other Week 1–3 activity
0.0.1 | Distribute KT document to all team members before first working session |  | High | 1 | 1 | Not Started | 0
0.0.2 | Walkthrough session: system architecture, tech stack, data model (2h, all team) |  | High | 1 | 1 | Not Started | 0
0.0.3 | Walkthrough session: working features demo — live run of key user journeys (2h, all team) |  | High | 1 | 1 | Not Started | 0 | Most important session — makes the architecture diagram click
0.0.4 | Walkthrough session: stubbed/incomplete features — what's fake, why, v1 plan (1h, all) |  | High | 1 | 1 | Not Started | 0
0.0.5 | Walkthrough session: AI ingestion pipeline deep-dive (2h, devs) |  | High | 2 | 2 | Not Started | 0
0.0.6 | Walkthrough session: ServiceNow integration — connection model, round-trip, Fluent notation (1h, devs) |  | Medium | 2 | 2 | Not Started | 0
0.0.7 | Individual developer setup: each dev gets local environment running against SQLite (half-day each) |  | High | 1 | 2 | Not Started | 0
0.0.8 | KT Q&A / open issues session and update KT document with answers (1h) |  | Medium | 3 | 3 | Not Started | 0
0.A | Azure Cloud Setup — Start Day 1 in Parallel |  |  | 1 | 4 | Not Started | 0 | Deloitte IT approvals take weeks — initiate immediately
0.A.1 | Identify Deloitte Azure subscription owner and request meeting within Week 1 |  | Critical | 1 | 1 | Not Started | 0
0.A.2 | Determine if Deloitte standard Azure landing zone applies (naming, policy, networking baseline) |  | High | 1 | 2 | Not Started | 0
0.A.3 | Submit Azure resource group provisioning request (dev environment first) |  | High | 1 | 2 | Not Started | 0
0.A.4 | Register application in Azure Entra ID — initiate with Deloitte IT (can take 2–4 weeks) |  | Critical | 1 | 4 | Not Started | 0 | CRITICAL PATH — gates all UAT and any real client usage
0.A.5 | Confirm Anthropic API vendor status in Deloitte procurement (pre-approved or CTU track?) |  | Critical | 1 | 2 | Not Started | 0 | CRITICAL PATH
0.A.6 | Identify CTU process owner and schedule intake call |  | Critical | 2 | 2 | Not Started | 0 | CRITICAL PATH
Phase 1 — IMMEDIATE RISK MITIGATION (Weeks 1–2)
0.1 | Data Integrity Fixes |  |  | 1 | 2 | Not Started | 0
0.1.1 | Wrap ingest promote and SN sync write-back in SQL transactions |  | Critical | 1 | 1 | Not Started | 0 | Issue #37 — server.js lines ~6943, ~7201
0.1.2 | Add Express global error middleware to replace bare 500s |  | Critical | 1 | 1 | Not Started | 0 | Issue #38 — no error middleware currently
0.1.3 | Fix migration loop error swallowing in db.js (catch {} hides schema failures) |  | High | 1 | 1 | Not Started | 0 | Issue #42
0.1.4 | Replace manual string escaping in /library with parameterized queries |  | Critical | 1 | 1 | Not Started | 0 | Issue #39 — SQL injection risk
0.2 | Security Hardening (Immediate) |  |  | 1 | 2 | Not Started | 0
0.2.1 | Make ASDLC_ENCRYPT_KEY required at startup — fail fast, no plaintext credential fallback |  | Critical | 1 | 1 | Not Started | 0 | Issue #76
0.2.2 | Strip ServiceNow error detail from client responses |  | High | 1 | 1 | Not Started | 0 | Issue #41 — SN instance URL leakage
0.2.3 | Add per-request project_id access validation stub (check asdlc_project_member) |  | High | 1 | 2 | Not Started | 0
0.3 | Database Performance Foundations |  |  | 1 | 2 | Not Started | 0
0.3.1 | Add missing indexes to schema (workflow_step, agent_spec, tool, other frequent-join columns) |  | High | 1 | 2 | Not Started | 0 | Issue #46
0.3.2 | Fix N+1 query loops in design-report endpoint (7 hot loops re-preparing identical statements) |  | High | 1 | 2 | Not Started | 0 | Issue #45
Phase 2 — FOUNDATION & SCOPING (Weeks 1–3)
1.1 | Product Scoping Workshop |  |  | 1 | 3 | Not Started | 0
1.1.1 | Inventory all 22 frontend modules and map each to MVP / Deferred (v2) / Cut |  | Critical | 1 | 2 | Not Started | 0
1.1.2 | Identify stub features — decide: implement or remove for v1 (Evidence Re-run, Reports Preview) |  | High | 1 | 2 | Not Started | 0
1.1.3 | Decide whether SN write-back (round-trip) is v1 or v2 |  | Critical | 2 | 2 | Not Started | 0 | Heaviest remaining feature
1.1.4 | Decide whether AI quality redesign (Suggestion Level slider, two-tier Sonnet+Opus) is v1 or v2 |  | High | 2 | 2 | Not Started | 0
1.1.5 | Define feature flags in code to gate deferred features without deleting them |  | Medium | 2 | 3 | Not Started | 0
1.1.6 | Produce written v1 scope document, signed off by project lead |  | Critical | 2 | 3 | Not Started | 0
1.2 | Architecture & Technology Decisions |  |  | 1 | 3 | Not Started | 0
1.2.1 | Select production database: Azure PostgreSQL vs. Azure SQL |  | Critical | 1 | 2 | Not Started | 0 | Recommendation: Azure PostgreSQL (cost + Prisma support)
1.2.2 | Decide ORM vs. raw queries: Prisma or Knex on top of existing parameterized SQL patterns |  | High | 1 | 2 | Not Started | 0 | 68 tables, no existing ORM
1.2.3 | Decide multi-tenancy enforcement model: app-layer tenant_id filtering vs. PostgreSQL RLS |  | High | 1 | 2 | Not Started | 0
1.2.4 | Decide containerization: Azure Container Apps (recommended) vs. Azure App Service |  | High | 1 | 2 | Not Started | 0
1.2.5 | Decide frontend path: keep Vanilla JS SPA vs. lightweight framework (v1 can stay Vanilla) |  | Medium | 2 | 3 | Not Started | 0
1.2.6 | Engage Deloitte IT on Azure Entra ID application registration requirements |  | Critical | 1 | 2 | Not Started | 0
1.2.7 | Confirm Anthropic API vendor status in Deloitte procurement |  | Critical | 1 | 2 | Not Started | 0
1.2.8 | Produce Architecture Decision Records (ADRs) for each major decision |  | High | 2 | 3 | Not Started | 0
1.3 | Project Foundations |  |  | 1 | 3 | Not Started | 0
1.3.1 | Git branching strategy: main (protected), staging, feature branches |  | High | 1 | 1 | Not Started | 0
1.3.2 | Set up project tracking board (one ticket per work plan activity) |  | High | 1 | 1 | Not Started | 0
1.3.3 | Standardize developer environment via devcontainer or setup.sh |  | High | 1 | 2 | Not Started | 0
1.3.4 | Define environment inventory: local → dev → staging → prod |  | High | 1 | 2 | Not Started | 0
1.3.5 | Assign workstream owners (auth, infra, testing, CTU) |  | Critical | 1 | 1 | Not Started | 0
Phase 3 — INFRASTRUCTURE & PLATFORM (Weeks 2–10)
2.1 | Azure Cloud Provisioning |  |  | 2 | 6 | Not Started | 0
2.1.1 | Identify Deloitte Azure tenant, subscription, and subscription owner |  | Critical | 2 | 2 | Not Started | 0 | CRITICAL PATH — start Week 2
2.1.2 | Determine if Deloitte standard Azure landing zone applies |  | High | 2 | 3 | Not Started | 0
2.1.3 | Provision resource groups for dev / staging / prod |  | Critical | 2 | 4 | Not Started | 0
2.1.4 | Configure virtual network, private endpoints, and outbound firewall rules |  | High | 3 | 5 | Not Started | 0
2.1.5 | Set up Azure Key Vault for all secrets (API keys, DB creds, ASDLC_ENCRYPT_KEY) |  | Critical | 3 | 5 | Not Started | 0
2.1.6 | Configure Azure Monitor + Log Analytics workspace |  | High | 4 | 6 | Not Started | 0
2.2 | Infrastructure as Code |  |  | 3 | 8 | Not Started | 0
2.2.1 | Choose IaC toolchain — Azure Bicep recommended for Deloitte Azure-native environments |  | High | 3 | 4 | Not Started | 0
2.2.2 | Write Bicep modules: compute, Azure PostgreSQL, networking, Key Vault, Container Registry |  | High | 4 | 7 | Not Started | 0
2.2.3 | Parameterize for environment promotion (dev / staging / prod configs) |  | High | 5 | 7 | Not Started | 0
2.2.4 | Store IaC under /infra in repo and wire to deployment pipeline |  | High | 6 | 8 | Not Started | 0
2.3 | Database Migration — SQLite → Azure PostgreSQL |  |  | 2 | 10 | Not Started | 0 | CRITICAL PATH — all feature work and performance testing blocks on this
2.3.1 | Audit all 68 tables in schema.sql for SQLite-specific syntax (type affinity, AUTOINCREMENT, JSON TEXT) |  | Critical | 2 | 3 | Not Started | 0
2.3.2 | Rewrite schema for PostgreSQL: proper types (uuid, jsonb, timestamptz), sequences, GENERATED ALWAYS |  | Critical | 3 | 5 | Not Started | 0
2.3.3 | Add client_id tenant column to any tables missing explicit client linkage |  | High | 3 | 4 | Not Started | 0
2.3.4 | Introduce ORM or migration tool: Prisma Migrate or Knex migrations |  | High | 3 | 5 | Not Started | 0
2.3.5 | Port all raw SQL in server.js to PostgreSQL-compatible parameterized queries |  | Critical | 4 | 9 | Not Started | 0 | Highest effort: 188 routes, ~9,935 lines
2.3.6 | Add application-layer tenant filtering: scopeToTenant() utility used in every route |  | Critical | 5 | 7 | Not Started | 0
2.3.7 | Write SQLite → PostgreSQL data migration script for existing dev/test datasets |  | High | 6 | 7 | Not Started | 0
2.3.8 | Connection pooling configuration (pg-pool or Prisma) and baseline load test |  | High | 7 | 9 | Not Started | 0
2.3.9 | Validate all 188 API routes against new database layer (automated regression) |  | Critical | 8 | 10 | Not Started | 0
2.4 | Application Containerization |  |  | 5 | 9 | Not Started | 0
2.4.1 | Write Dockerfile for Node.js Express backend (docker-compose.yml already exists — extend it) |  | High | 5 | 6 | Not Started | 0
2.4.2 | Write nginx.conf or static file serving for Vanilla JS frontend (or serve from Express) |  | Medium | 5 | 7 | Not Started | 0
2.4.3 | Multi-stage build: dependencies → build → runtime image |  | High | 6 | 7 | Not Started | 0
2.4.4 | Push to Azure Container Registry |  | High | 7 | 9 | Not Started | 0
2.5 | CI/CD Pipeline |  |  | 6 | 10 | Not Started | 0
2.5.1 | Set up GitHub Actions build pipeline: lint → unit tests → build → container image push |  | High | 6 | 8 | Not Started | 0
2.5.2 | Set up deployment pipeline: dev → staging → prod (manual approval gate before prod) |  | High | 7 | 9 | Not Started | 0
2.5.3 | Configure Azure Key Vault secret injection into container env vars |  | High | 7 | 9 | Not Started | 0
2.5.4 | Define and test rollback procedure (redeploy previous container tag) |  | High | 8 | 10 | Not Started | 0
2.5.5 | Add pipeline status badge to repo README |  | Low | 9 | 10 | Not Started | 0
Phase 4 — AUTHENTICATION, AUTHORIZATION & MULTI-TENANCY (Weeks 4–10)
3.1 | Authentication — start from scratch |  |  | 4 | 8 | Not Started | 0 | Currently just X-User-ID header — no real auth exists
3.1.1 | Register application in Azure Entra ID (requires Deloitte IT engagement) |  | Critical | 3 | 6 | Not Started | 0 | CRITICAL PATH — start Week 3; gates all UAT and client use
3.1.2 | Implement OIDC/OAuth2 login flow (Microsoft identity platform / MSAL) |  | Critical | 5 | 8 | Not Started | 0
3.1.3 | Replace localStorage user ID with proper JWT session (access token + refresh token) |  | Critical | 5 | 8 | Not Started | 0
3.1.4 | Update apiFetch() in app.js to send Authorization: Bearer token instead of X-User-ID header |  | High | 6 | 8 | Not Started | 0
3.1.5 | Add server-side JWT verification middleware (replace line 103 X-User-ID extraction in server.js) |  | Critical | 6 | 8 | Not Started | 0
3.1.6 | Handle Deloitte-internal vs. external client users (Entra B2B guest accounts or federated IdP) |  | High | 6 | 9 | Not Started | 0
3.1.7 | Implement logout, token revocation, and idle session timeout |  | High | 7 | 9 | Not Started | 0
3.1.8 | Add CSRF protection and tighten CORS from wildcard * to allowed origins |  | Critical | 6 | 8 | Not Started | 0
3.2 | Role-Based Access Control (RBAC) |  |  | 6 | 10 | Not Started | 0
3.2.1 | Define role taxonomy: Platform Admin / Client Admin / Analyst / Viewer |  | High | 6 | 7 | Not Started | 0
3.2.2 | Implement requiresRole() middleware applied to every route group in server.js |  | Critical | 7 | 9 | Not Started | 0
3.2.3 | Implement requiresProjectAccess() middleware — verify user has row in asdlc_project_member |  | Critical | 7 | 9 | Not Started | 0
3.2.4 | Add role management UI in admin panel (admin_ai.js or new admin_users.js module) |  | High | 8 | 10 | Not Started | 0
3.2.5 | Audit every one of the 188 routes for appropriate role requirement |  | Critical | 8 | 10 | Not Started | 0
3.3 | Client & Tenant Data Isolation |  |  | 7 | 10 | Not Started | 0
3.3.1 | Implement tenant context middleware: extract client_id from authenticated user's JWT claims |  | Critical | 7 | 9 | Not Started | 0
3.3.2 | Apply scopeToTenant() utility on every database query |  | Critical | 7 | 10 | Not Started | 0
3.3.3 | Write automated cross-tenant isolation test suite (tenant A cannot read/write tenant B data) |  | Critical | 8 | 10 | Not Started | 0
3.3.4 | Implement client onboarding flow: create asdlc_client → assign Client Admin → configure SN |  | High | 8 | 10 | Not Started | 0
3.3.5 | Implement client deprovisioning: data deletion or archival, user removal |  | Medium | 9 | 10 | Not Started | 0
3.4 | User Management |  |  | 8 | 10 | Not Started | 0
3.4.1 | User invitation flow (email invite or SSO just-in-time provisioning) |  | High | 8 | 10 | Not Started | 0
3.4.2 | Client admin UI for user management (invite, role assignment, deactivate) |  | High | 8 | 10 | Not Started | 0
3.4.3 | Platform admin UI for cross-client user overview |  | Medium | 9 | 10 | Not Started | 0
3.4.4 | Full user-action audit log wired to asdlc_audit_log (ensure auth events captured) |  | High | 8 | 10 | Not Started | 0
Phase 5 — SERVER MODULARIZATION & FEATURE COMPLETION (Weeks 4–14)
4.1 | Server.js Refactoring — Technical Debt #44 |  |  | 3 | 8 | Not Started | 0 | CRITICAL PATH — 9,935-line monolith blocks parallel development
4.1.1 | Extract route groups into separate files under backend-node/routes/ (one file per domain) |  | Critical | 3 | 6 | Not Started | 0 | Projects, ingest, design, servicenow, cost, admin
4.1.2 | Extract agent/AI orchestration logic into backend-node/agent/ submodules |  | High | 4 | 7 | Not Started | 0
4.1.3 | Extract shared DB utilities from monolith into backend-node/db/ modules |  | High | 4 | 7 | Not Started | 0
4.1.4 | Verify all 188 routes still pass after modularization (regression test) |  | Critical | 6 | 8 | Not Started | 0
4.2 | Technical Debt Triage & Cleanup |  |  | 4 | 10 | Not Started | 0
4.2.1 | Remove or feature-flag all non-MVP functionality identified in Phase 1 scoping |  | High | 4 | 6 | Not Started | 0
4.2.2 | Remove stub buttons and replace with 'coming in v2' messaging (Evidence, Reports stubs) |  | Medium | 4 | 6 | Not Started | 0
4.2.3 | Audit all hardcoded values and move to environment variables (Issue #43 — hardcoded model name) |  | High | 4 | 7 | Not Started | 0
4.2.4 | Remove SN_INSECURE_TLS bypass for production; implement NODE_EXTRA_CA_CERTS with Deloitte proxy cert |  | Critical | 5 | 7 | Not Started | 0
4.2.5 | Add startup validation: required env vars checked at boot, fail fast with clear message |  | High | 4 | 6 | Not Started | 0
4.2.6 | Fix seed data: remove seed.js auto-run on startup (or make it dev-only) |  | Medium | 4 | 6 | Not Started | 0
4.3 | AI Ingestion Pipeline Hardening |  |  | 5 | 11 | Not Started | 0
4.3.1 | Add retry logic and circuit breaker for Anthropic API failures (currently unhandled) |  | High | 5 | 8 | Not Started | 0
4.3.2 | Per-tenant AI cost tracking and budget alerting (expand asdlc_ai_usage table) |  | High | 6 | 9 | Not Started | 0
4.3.3 | Add PDF ingest support (Issue #64 — currently falls through to UTF-8 read, produces garbage) |  | High | 7 | 10 | Not Started | 0 | Needs pdfjs or similar PDF-to-text library
4.3.4 | Implement Suggestion Level slider (confidence threshold) — if scoped to v1 |  | Medium | 8 | 11 | Not Started | 0
4.3.5 | Validate and fix RASIC auto-population (Issue #36 — recurring AI regression) |  | High | 5 | 8 | Not Started | 0
4.3.6 | Fix clarification auto-apply overwriting cost params project-wide (Issue #40) |  | High | 5 | 7 | Not Started | 0
4.4 | ServiceNow Integration Hardening |  |  | 6 | 12 | Not Started | 0
4.4.1 | Make all SN connection parameters configurable per tenant via Key Vault (not .env fallback) |  | High | 6 | 8 | Not Started | 0
4.4.2 | Complete SN sys_id write-back (round-trip) — if scoped to v1 |  | High | 7 | 12 | Not Started | 0
4.4.3 | Add net-new conflict detection (changes in SN since last ingest) |  | High | 8 | 12 | Not Started | 0
4.4.4 | Handle SN API rate limits and timeouts gracefully |  | High | 7 | 9 | Not Started | 0
4.4.5 | Validate Build Spec generation end-to-end against a real SN dev instance |  | High | 9 | 12 | Not Started | 0
4.5 | Frontend Polish & Bug Fixes |  |  | 5 | 12 | Not Started | 0
4.5.1 | Fix change-packet action buttons staying active after terminal action (Issue #17) |  | High | 5 | 6 | Not Started | 0
4.5.2 | Fix baseline detail fetch using wrong ID field — undefined (Issue #49) |  | High | 5 | 6 | Not Started | 0
4.5.3 | Fix cost management modal missing CSS classes (Issue #51) |  | Medium | 5 | 6 | Not Started | 0
4.5.4 | Add debounce to search filters — currently O(rows × payload) per keystroke (Issue #58) |  | Medium | 6 | 8 | Not Started | 0
4.5.5 | Fix SN-conflict approval silently dropping accepted value (Issue #62) |  | High | 6 | 8 | Not Started | 0
4.5.6 | Fix testing.js assuming unpaginated /projects response (Issue #54) |  | High | 5 | 7 | Not Started | 0
4.5.7 | Consistent error handling and user-facing messages across all 22 modules |  | High | 7 | 10 | Not Started | 0
4.5.8 | Loading states and progress indicators for long-running AI operations |  | Medium | 8 | 12 | Not Started | 0
Phase 6 — TESTING (Weeks 6–16)
5.1 | Test Strategy & Infrastructure |  |  | 6 | 9 | Not Started | 0
5.1.1 | Write test plan document covering scope, types, tooling, and pass criteria |  | High | 6 | 7 | Not Started | 0
5.1.2 | Select and configure test runner — Jest or Vitest (currently no runner; package.json test = echo) |  | Critical | 6 | 7 | Not Started | 0
5.1.3 | Set up test database: isolated PostgreSQL instance seeded with fixtures |  | Critical | 6 | 8 | Not Started | 0
5.1.4 | Define test data management policy (synthetic data only; no real client data in test environments) |  | High | 6 | 8 | Not Started | 0
5.1.5 | Add coverage reporting to CI pipeline (target: 70% line coverage on business logic) |  | High | 7 | 9 | Not Started | 0
5.2 | Unit Tests |  |  | 7 | 12 | Not Started | 0
5.2.1 | Unit tests for db.js helper functions (generateId, nextSlug, auditLog, scopeToTenant) |  | High | 7 | 9 | Not Started | 0
5.2.2 | Unit tests for AI ingestion pipeline modules (agent/) |  | High | 7 | 10 | Not Started | 0
5.2.3 | Unit tests for cost mapping and rate card logic |  | High | 7 | 10 | Not Started | 0
5.2.4 | Unit tests for auth middleware and RBAC enforcement |  | Critical | 8 | 11 | Not Started | 0
5.2.5 | Unit tests for SN integration utilities (provenance, sys_id mapping, Fluent notation) |  | High | 8 | 11 | Not Started | 0
5.2.6 | Organize and add assertions to the 11 existing test-*.js files where they contain useful scenarios |  | Medium | 7 | 10 | Not Started | 0
5.3 | Integration Tests |  |  | 8 | 14 | Not Started | 0
5.3.1 | API integration test suite for all 188 endpoints (auth, CRUD, AI operations) |  | Critical | 8 | 12 | Not Started | 0
5.3.2 | Database integration tests: multi-tenant isolation, transaction rollback, FK enforcement |  | Critical | 8 | 12 | Not Started | 0
5.3.3 | AI pipeline integration tests (mocked Anthropic API + real PostgreSQL) |  | High | 9 | 12 | Not Started | 0
5.3.4 | ServiceNow integration tests (against a SN dev instance) |  | High | 9 | 13 | Not Started | 0
5.3.5 | Cross-tenant isolation tests: tenant A cannot read/write tenant B records on any endpoint |  | Critical | 9 | 13 | Not Started | 0
5.4 | End-to-End Tests |  |  | 10 | 14 | Not Started | 0
5.4.1 | Select E2E framework — Playwright recommended (works with Vanilla JS SPA) |  | High | 10 | 11 | Not Started | 0
5.4.2 | Core analyst journey E2E: login → select project → ingest SN app → review design → export |  | Critical | 10 | 13 | Not Started | 0
5.4.3 | Admin journey E2E: login as Client Admin → create project → invite user → configure SN → assign role |  | High | 11 | 13 | Not Started | 0
5.4.4 | SN round-trip E2E: ingest → edit design → write-back → verify change in SN instance |  | High | 11 | 14 | Not Started | 0
5.4.5 | Cross-tenant isolation E2E: user from tenant A cannot navigate to tenant B data via URL manipulation |  | Critical | 12 | 14 | Not Started | 0
5.5 | Performance & Load Testing |  |  | 11 | 15 | Not Started | 0
5.5.1 | Define performance targets (API p95 latency, AI operation timeout budgets, concurrent user count) |  | High | 11 | 12 | Not Started | 0
5.5.2 | Load test concurrent user scenarios against PostgreSQL (baseline before and after optimizations) |  | High | 12 | 14 | Not Started | 0
5.5.3 | AI pipeline cost and latency profiling under load (Anthropic API rate limits) |  | High | 12 | 14 | Not Started | 0
5.5.4 | PostgreSQL query performance analysis and index optimization |  | High | 12 | 14 | Not Started | 0
5.5.5 | Document baselines in ARCHITECTURE.md for ongoing regression tracking |  | Medium | 13 | 15 | Not Started | 0
5.6 | User Acceptance Testing (UAT) |  |  | 12 | 16 | Not Started | 0
5.6.1 | Write UAT test scripts for all MVP features |  | High | 12 | 13 | Not Started | 0
5.6.2 | Internal pilot: run against a real Deloitte-internal SN instance with the project team |  | Critical | 13 | 15 | Not Started | 0
5.6.3 | Triage UAT findings: P1 (must fix) / P2 (should fix) / P3 (v2) |  | High | 14 | 15 | Not Started | 0
5.6.4 | Resolve all P1 and targeted P2 issues |  | Critical | 14 | 16 | Not Started | 0
5.6.5 | Formal UAT sign-off from project lead |  | Critical | 15 | 16 | Not Started | 0
Phase 7 — SECURITY & CERTIFIED TO USE (CTU) (Weeks 3–16)
6.1 | Security Self-Assessment |  |  | 3 | 7 | Not Started | 0
6.1.1 | Produce threat model document: data flows, trust boundaries, threat actors, data classification |  | Critical | 3 | 5 | Not Started | 0
6.1.2 | OWASP Top 10 self-assessment against codebase (focus: auth gap, SQL injection, CORS) |  | Critical | 3 | 6 | Not Started | 0
6.1.3 | LLM/AI-specific security review: prompt injection, client data leakage into AI prompts, output validation |  | High | 4 | 6 | Not Started | 0
6.1.4 | Secrets audit: confirm no API keys, credentials, or tokens in source code, logs, or error responses |  | Critical | 3 | 5 | Not Started | 0
6.1.5 | npm dependency vulnerability scan (npm audit + Snyk) and remediation |  | High | 3 | 5 | Not Started | 0
6.1.6 | Remediate all critical findings before InfoSec submission |  | Critical | 5 | 7 | Not Started | 0
6.2 | Deloitte InfoSec Review |  |  | 6 | 12 | Not Started | 0
6.2.1 | Identify Deloitte InfoSec / CISO team contact for application security reviews |  | Critical | 3 | 4 | Not Started | 0
6.2.2 | Complete Deloitte security questionnaire / application security intake |  | Critical | 6 | 8 | Not Started | 0
6.2.3 | Provide architecture diagram, data flow diagrams, and threat model to InfoSec |  | High | 6 | 8 | Not Started | 0
6.2.4 | Schedule penetration test if required by CTU process |  | High | 7 | 10 | Not Started | 0
6.2.5 | Remediate all critical and high findings from InfoSec review |  | Critical | 9 | 12 | Not Started | 0
6.2.6 | Obtain InfoSec sign-off |  | Critical | 11 | 12 | Not Started | 0
6.3 | Data Privacy & Legal Review |  |  | 5 | 13 | Not Started | 0
6.3.1 | Identify all personal data and client confidential data processed (user emails, SN design, AI I/O) |  | High | 5 | 7 | Not Started | 0
6.3.2 | Complete Data Privacy Impact Assessment (DPIA) |  | Critical | 7 | 10 | Not Started | 0
6.3.3 | Define and implement data retention, deletion, and portability policies |  | High | 8 | 11 | Not Started | 0
6.3.4 | Review Anthropic API terms of service for client data handling (residency, training opt-out, DPA) |  | Critical | 5 | 7 | Not Started | 0
6.3.5 | Engage Deloitte Legal on IP ownership and liability for a Deloitte-managed AI tool |  | Critical | 5 | 8 | Not Started | 0
6.3.6 | Obtain Legal sign-off on data handling and IP |  | Critical | 10 | 13 | Not Started | 0
6.4 | CTU Certification Submission |  |  | 2 | 16 | Not Started | 0 | Procurement and legal reviews take months; submissions cannot be rushed
6.4.1 | Identify CTU process owner and required submission package components |  | Critical | 2 | 3 | Not Started | 0 | CRITICAL PATH — start Week 2
6.4.2 | Confirm Anthropic API vendor status in Deloitte procurement (pre-approved or new CTU vendor track) |  | Critical | 2 | 4 | Not Started | 0 | CRITICAL PATH — start Week 2
6.4.3 | Complete vendor approval for other third-party services (Azure, mammoth, docx libraries) |  | High | 5 | 8 | Not Started | 0
6.4.4 | Compile tool risk assessment document |  | High | 8 | 11 | Not Started | 0
6.4.5 | Submit full CTU package: risk assessment + InfoSec + Legal + DPIA + vendor approvals |  | Critical | 12 | 13 | Not Started | 0
6.4.6 | Respond to CTU reviewer questions and requested changes |  | Critical | 13 | 15 | Not Started | 0
6.4.7 | Receive, file, and communicate CTU approval certificate |  | Critical | 15 | 16 | Not Started | 0
Phase 8 — OBSERVABILITY & OPERATIONS (Weeks 8–16)
7.1 | Monitoring & Alerting |  |  | 8 | 12 | Not Started | 0
7.1.1 | Configure Azure Application Insights (APM) on the Node.js process |  | High | 8 | 10 | Not Started | 0
7.1.2 | Set up error rate, latency, and availability alerts with PagerDuty or email notification |  | High | 9 | 11 | Not Started | 0
7.1.3 | AI pipeline cost and token usage dashboards (expand asdlc_ai_usage into Azure Monitor) |  | Medium | 9 | 12 | Not Started | 0
7.1.4 | PostgreSQL performance monitoring (slow queries, connection pool saturation) |  | High | 9 | 12 | Not Started | 0
7.1.5 | Uptime / SLA dashboard |  | Medium | 10 | 12 | Not Started | 0
7.2 | Logging & Audit Trail |  |  | 8 | 13 | Not Started | 0
7.2.1 | Implement structured JSON logging (Winston or Pino) — replace console.log calls in server.js |  | High | 8 | 10 | Not Started | 0
7.2.2 | Confirm no PII, credentials, or SN error details appear in logs (Issue #41 — partially broken) |  | Critical | 8 | 10 | Not Started | 0
7.2.3 | Wire authentication events (login, logout, failed auth) to asdlc_audit_log |  | High | 9 | 11 | Not Started | 0
7.2.4 | Configure log retention policy aligned with data privacy requirements |  | High | 10 | 12 | Not Started | 0
7.2.5 | Set up log search and alerting via Log Analytics |  | Medium | 10 | 13 | Not Started | 0
7.3 | Runbooks & Support Documentation |  |  | 10 | 15 | Not Started | 0
7.3.1 | Deployment runbook (deploy, roll back, hotfix) |  | High | 10 | 12 | Not Started | 0
7.3.2 | Incident response runbook (triage, escalate, communicate, post-mortem) |  | High | 10 | 12 | Not Started | 0
7.3.3 | Common operational procedures (restart, scale, re-run failed ingestion, clear stuck queue item) |  | High | 11 | 13 | Not Started | 0
7.3.4 | Known issues and FAQ for support team |  | Medium | 11 | 14 | Not Started | 0
7.3.5 | On-call rotation setup and escalation path |  | High | 12 | 15 | Not Started | 0
7.4 | Backup & Recovery |  |  | 10 | 14 | Not Started | 0
7.4.1 | Configure automated Azure PostgreSQL backups (PITR, minimum 7-day retention) |  | Critical | 10 | 12 | Not Started | 0
7.4.2 | Define and test Recovery Time Objective (RTO) and Recovery Point Objective (RPO) |  | High | 11 | 13 | Not Started | 0
7.4.3 | Document disaster recovery procedure |  | High | 12 | 14 | Not Started | 0
7.4.4 | Schedule and execute a backup restoration drill before GA |  | Critical | 13 | 14 | Not Started | 0
Phase 9 — DOCUMENTATION & ENABLEMENT (Weeks 10–18)
8.1 | Technical Documentation |  |  | 10 | 16 | Not Started | 0
8.1.1 | Architecture document: system overview, component diagram, data flows (extend ARCHITECTURE.md) |  | High | 10 | 14 | Not Started | 0
8.1.2 | API reference: all 188 endpoints, auth, request/response schemas |  | High | 10 | 15 | Not Started | 0
8.1.3 | Database schema documentation: all 68 tables, key relationships, multi-tenancy model |  | High | 11 | 15 | Not Started | 0
8.1.4 | Developer onboarding guide: local setup, test run, deploy process |  | High | 12 | 15 | Not Started | 0
8.1.5 | AI ingestion design guide: how prompts work in agent/prompts/*.md, how to extend or modify |  | Medium | 12 | 16 | Not Started | 0
8.2 | End-User Documentation |  |  | 12 | 17 | Not Started | 0
8.2.1 | User guide: ingesting a ServiceNow application |  | High | 12 | 15 | Not Started | 0
8.2.2 | User guide: reviewing and editing a design in the Workbench |  | High | 12 | 16 | Not Started | 0
8.2.3 | User guide: the SN round-trip (edit → write-back) — if in v1 scope |  | Medium | 13 | 17 | Not Started | 0
8.2.4 | Client admin guide: user management, project setup, SN configuration |  | High | 13 | 17 | Not Started | 0
8.2.5 | Platform admin guide: tenant management, monitoring, cost control |  | High | 13 | 17 | Not Started | 0
8.3 | Client Onboarding Package |  |  | 14 | 18 | Not Started | 0
8.3.1 | Client onboarding checklist (SN credentials, user list, roles, project setup steps) |  | High | 14 | 17 | Not Started | 0
8.3.2 | Client-facing one-pager / tool overview for engagement kickoff |  | Medium | 14 | 17 | Not Started | 0
8.3.3 | Training materials and demo script for client onboarding call |  | High | 15 | 18 | Not Started | 0
Phase 10 — PILOT LAUNCH & GENERAL AVAILABILITY (Weeks 16–24)
9.1 | Internal Pilot |  |  | 16 | 20 | Not Started | 0
9.1.1 | Select pilot — Deloitte-internal project or low-risk client with a known SN environment |  | Critical | 16 | 17 | Not Started | 0
9.1.2 | Stand up pilot tenant and onboard users |  | Critical | 17 | 18 | Not Started | 0
9.1.3 | Run structured pilot sessions with facilitated feedback capture |  | Critical | 18 | 19 | Not Started | 0
9.1.4 | Triage pilot feedback; implement priority fixes in a dedicated stabilization sprint |  | Critical | 19 | 20 | Not Started | 0
9.1.5 | Pilot retrospective and go/no-go decision for general availability |  | Critical | 20 | 20 | Not Started | 0
9.2 | General Availability Preparation |  |  | 18 | 22 | Not Started | 0
9.2.1 | Define GA release criteria: scope complete + CTU approved + InfoSec clear + UAT signed off |  | Critical | 18 | 20 | Not Started | 0
9.2.2 | Staged rollout plan: 1 client → 3 clients → open intake |  | High | 19 | 21 | Not Started | 0
9.2.3 | Rollback plan for production issues (specific container tag + DB restore procedure) |  | High | 19 | 21 | Not Started | 0
9.2.4 | Internal communications to practice/sector leads |  | Medium | 20 | 22 | Not Started | 0
9.2.5 | Client intake process: how engagement teams request access |  | High | 20 | 22 | Not Started | 0
9.3 | Post-Launch Stabilization |  |  | 21 | 24 | Not Started | 0
9.3.1 | Hyper-care period: daily standups, rapid-response SLA, 2-week window post-GA |  | Critical | 21 | 22 | Not Started | 0
9.3.2 | Bug triage and priority fix cycles |  | High | 21 | 24 | Not Started | 0
9.3.3 | Collect early client feedback and feed into v2 backlog |  | High | 22 | 24 | Not Started | 0
9.3.4 | Transition to steady-state support model |  | High | 23 | 24 | Not Started | 0

## Summary
Phase | Phase Name | Start Wk | End Wk | Workstreams | Activities | Owner | Status | Notes
0 | Start Immediately & Run in Parallel | 1 | 4 | 2 | 17 | Critical | Not Started | KT sessions + Azure setup — start Day 1, run in parallel
1 | Immediate Risk Mitigation | 1 | 2 | 3 | 10 | Critical | Not Started | 7 critical defects; 1–2 dev-weeks
2 | Foundation & Scoping | 1 | 3 | 3 | 21 | Critical | Not Started | Scoping workshop + ADRs + project setup
3 | Infrastructure & Platform | 2 | 10 | 5 | 32 | High | Not Started | Azure provisioning, IaC, DB migration, containerization, CI/CD
4 | Authentication, Authorization & Multi-Tenancy | 4 | 10 | 4 | 22 | Critical | Not Started | Auth from scratch; RBAC; tenant isolation
5 | Server Modularization & Feature Completion | 4 | 14 | 5 | 35 | Critical | Not Started | Split 9,935-line monolith; tech debt; AI/SN hardening; frontend fixes
6 | Testing | 6 | 16 | 6 | 32 | High | Not Started | Unit, integration, E2E, performance, UAT
7 | Security & CTU | 3 | 16 | 4 | 25 | Critical | Not Started | Start CTU in Weeks 3–5 — it is on the critical path
8 | Observability & Operations | 8 | 16 | 4 | 20 | High | Not Started | Azure App Insights, logging, runbooks, backups
9 | Documentation & Enablement | 10 | 18 | 3 | 14 | High | Not Started | Technical, end-user, and client onboarding docs
10 | Pilot Launch & General Availability | 16 | 24 | 3 | 14 | Critical | Not Started | Internal pilot → staged GA → post-launch stabilization
Rough Timeline (3–6 Month View)
Weeks 1–2 | Phase 0 (fast wins) + Phase 1 (risk mitigation) + Phase 2 (scoping) + initiate CTU/Azure
Weeks 3–6 | Phase 3 (infra + DB migration) + Phase 4 (auth) + Phase 5 begin (server modularization)
Weeks 6–10 | Phase 5 (feature completion) + Phase 6.1–6.3 (unit + integration tests) + Phase 7 (security review)
Weeks 10–14 | Phase 6.4–6.6 (E2E + UAT) + Phase 7.4 (CTU submission) + Phase 8 (observability)
Weeks 14–18 | Phase 9 (documentation) + Phase 10.1 (internal pilot)
Weeks 18–22 | Phase 10.2–10.3 (GA preparation + post-launch stabilization)
At 2 developers: 20–22 weeks (tight for 6 months) ¦ At 4 developers with parallel workstreams: 14–16 weeks comfortably

## Critical Path
# | Critical Path Item | Activity ID | Start By | Owner | Why It Blocks
⚠ Delays in ANY of these items slip the launch date. Start these in parallel with everything else on Day 1.
1 | CTU engagement | 6.4.1 | Week 2 |  | Procurement and legal reviews take months; submissions cannot be rushed
2 | Anthropic vendor approval | 6.4.2 | Week 2 |  | May need to go through Deloitte procurement if not pre-approved
3 | Azure provisioning + Deloitte IT | 2.1.1 | Week 2 |  | Deloitte IT approvals and landing zone setup take time
4 | Azure Entra ID registration | 3.1.1 | Week 3 |  | Auth gates all UAT and any real client usage
5 | Database migration (SQLite → PostgreSQL) | 2.3 | Week 2 |  | All feature work and performance testing blocks on this
6 | Server.js modularization | 4.1.1 | Week 3 |  | 9,935-line monolith causes merge conflicts with 2–4 devs working in parallel

## Open Questions
# | Question | Owner | Due Date | Answer / Decision | Status
1 | Is Anthropic already a pre-approved vendor in Deloitte procurement, or does it need a new CTU vendor track? |  |  |  | Open
2 | What are the specific steps and typical timeline for CTU at Deloitte? |  |  |  | Open
3 | Does a Deloitte Azure landing zone standard apply? If so, who owns the subscription? |  |  |  | Open
4 | Do external client users log in via Entra B2B guest accounts or via federated client IdP? |  |  |  | Open
5 | Is the SN write-back (round-trip) in scope for v1 or v2? |  |  |  | Open
6 | Does Deloitte require data residency (e.g. EU data must stay in EU Azure regions)? |  |  |  | Open
Resolve these questions in the Phase 2 scoping workshop (Weeks 1–3). Answers directly affect the v1 scope, architecture decisions, and CTU timeline.